## Summary
Project Audit | Khalasni project audit backlog
Audit Date | 2026-05-05
Scope | Backend Django APIs, frontend React app, role-based operational flow, local demo environment
Main Finding | The core multi-role workflow exists, but demo/live local data contamination, silent frontend fallbacks, and missing UX/state automation still create confusion.
Open Problems Count | 12
Enhancement Opportunities Count | 12
Environment / Data Findings Count | 6
Important Note | This sheet includes codebase issues plus local environment/data issues found during the audit.

## Problems
ID | Area | Severity | Status | Problem | Impact | Evidence / Location | Recommended Action
P-001 | Frontend API layer | High | Open | Silent mock / fallback responses still exist on many pages, so some API failures can be hidden by fake data. | Users and testers may think the system works while the backend call actually failed. | frontend/src/api/services.js | Remove fallback behavior outside explicit test/dev mode and surface real API errors in the UI.
P-002 | Configuration | Medium | Open | Frontend API base URL is hardcoded to localhost fallback and there are no checked-in frontend env templates. | Deployment and environment switching remain fragile and easy to misconfigure. | frontend/src/api/client.js; no frontend/.env or frontend/.env.local present | Add .env.example and make environments explicit for dev, staging, and production.
P-003 | Local data hygiene | High | Open | Temporary debug provider accounts and debug orders remain in the live local database. | Operational testing can target the wrong provider account and produce false workflow failures. | provider-debug@example.com, provider-debug-2@example.com, provider-debug-3@example.com; orders KH-2026-000005 and KH-2026-000006 | Clean debug accounts/orders and add a safe reset command for demo data.
P-004 | Demo environment | Medium | Open | There is no one-command reset/seed workflow for a known-clean demo state. | Each test cycle can drift from the expected system state. | Observed from local DB usage pattern and existing seed/debug data | Add commands for reset_demo_data and seed_demo_data with documented credentials.
P-005 | Frontend build performance | Medium | Open | Production build still emits a large JS chunk warning (>500 kB after minification). | Slower load time and higher risk on lower-end devices or weak connections. | npm run build output for frontend | Introduce route-level code splitting and trim heavy shared bundles.
P-006 | Employee workflow UX | Medium | Open | The employee review page still relies on the user understanding multiple implicit states instead of showing a clear readiness panel. | Employees can be unsure why assignment is or is not allowed. | frontend/src/pages/employee/EmployeeOrderReviewPage.jsx | Add a visible checklist: required docs, approval state, assignability, next action.
P-007 | Document verification flow | Medium | Open | Approving documents does not automatically move the order to an explicitly ready-for-assignment state from the verification screen. | Users must navigate back manually and infer the next step. | frontend/src/pages/employee/EmployeeVerifyDocumentsPage.jsx; backend/documents/services.py | Add workflow automation or a clear CTA after all required documents are approved.
P-008 | Testing strategy | High | Open | There is no browser-level end-to-end automation for the real customer -> employee -> provider -> admin lifecycle. | Cross-role regressions can pass unit/API tests but still fail in the actual UI flow. | Frontend has Vitest page tests; backend has Django tests; no E2E suite present | Add Playwright or Cypress scenarios for the full operational flow.
P-009 | Frontend coverage | Medium | Open | Frontend test coverage is concentrated on a few fixed pages; many admin/customer/provider pages still have no direct regression tests. | UI regressions may escape until manual testing. | Limited *.test.jsx files under frontend/src/pages | Expand test coverage by critical screen and role.
P-010 | Backend response text | Low | Open | The public create-order API success message contains mojibake/garbled Arabic in the backend response payload. | Customer-facing or integrator-facing messages can look broken even when the operation succeeds. | backend/orders/views.py CreateOrderAPIView response message | Normalize the success message encoding and audit other static Arabic strings in backend responses.
P-011 | Architecture / rules ownership | Medium | Open | Workflow rules are split between backend permission/transition logic and frontend UI assumptions. | Screens can drift from backend behavior and block valid actions or allow invalid ones. | backend/workflow/transition_permissions.py; frontend employee/provider pages | Centralize business-state rules in backend and have frontend render capability from API state.
P-012 | Operational observability | Medium | Open | The project has limited operator-facing visibility into why an order is blocked, who was notified, and what action is pending next. | Support/debug time is longer and user-facing failures are harder to explain. | Current pages show status/timeline but not a consolidated blocker/explanation panel | Add a workflow diagnostics section per order with blockers, missing approvals, and notification history.

## Enhancements
ID | Area | Priority | Opportunity | Value | Recommended Enhancement | Dependencies / Notes
E-001 | Demo environment | High | Create a clean demo reset + reseed workflow. | Makes testing repeatable and removes data drift. | Add management commands to wipe debug data and reseed demo users/providers/orders. | Should preserve optional backups or require explicit confirmation.
E-002 | E2E QA | High | Automate the full service flow across roles. | Prevents repeat regressions in real user journeys. | Add Playwright/Cypress coverage for create order, approve docs, assign provider, provider execution, final completion. | Use seeded demo data and stable test fixtures.
E-003 | Employee UX | High | Show order readiness before assignment. | Removes guesswork for the employee role. | Display required documents, approval status, missing items, and whether assignment is currently allowed. | Can be derived from service requirements + document statuses.
E-004 | Workflow automation | Medium | Auto-mark orders as ready for provider assignment once all required docs are approved. | Reduces manual steps and state confusion. | Introduce an explicit internal state or a computed readiness flag returned by the API. | Keep final assignment as a staff action.
E-005 | Provider selection | Medium | Improve provider assignment UI. | Better provider choice quality and lower misassignment risk. | Add filtering by city, workload, rating, and service match in the employee assignment panel. | Now filtered by order, but still basic in UI.
E-006 | Notifications | Medium | Make notifications more actionable. | Users can move directly from notification to the exact order/action. | Add deep links and role-specific notification inbox improvements. | Customer/provider/admin all benefit.
E-007 | API reliability | High | Eliminate silent fallbacks from real runtime. | Makes failures obvious and easier to debug. | Restrict mock data to tests only or explicit offline mode. | Requires UX for error states/loading states.
E-008 | Configuration management | Medium | Add environment templates and startup validation. | Reduces environment mistakes. | Create frontend/backend .env.example files and warn when required settings are missing. | Also document ports and expected services.
E-009 | Performance | Medium | Reduce frontend bundle size. | Improves first load and caching behavior. | Use route-based lazy loading and review large shared dependencies. | Current build already warns on chunk size.
E-010 | Reporting | Low | Exportable operational audit reports. | Useful for admins and support tracking. | Add CSV/XLSX export for orders, notification logs, and workflow blockers. | Can reuse current reports/audit endpoints.
E-011 | Order diagnostics | Medium | Add a per-order system health panel. | Makes stuck orders easier to understand. | Expose assigned actor, required docs status, last notification sent, and next valid actions. | Useful for employee/admin screens.
E-012 | Data governance | Medium | Guard against accidental debug data in shared environments. | Reduces contamination and confusing test outcomes. | Tag debug/demo objects clearly and provide cleanup scripts plus naming rules. | Should include debug users, providers, services, and orders.

## Env_Data
ID | Category | Current Finding | Evidence | Risk | Action
D-001 | Provider Accounts | Demo provider account exists alongside three temporary debug provider accounts. | provider@khalasni.local plus provider-debug@example.com, provider-debug-2@example.com, provider-debug-3@example.com | Assignments and notifications can hit the wrong account during manual testing. | Clean debug providers or isolate them under a separate demo profile set.
D-002 | Orders | Local DB contains debug orders assigned to debug providers. | KH-2026-000005 and KH-2026-000006 assigned to provider-debug accounts | Provider-side testing can appear broken if the tester logs into the demo provider instead of the debug provider. | Archive/delete debug orders or move them to a dedicated debug dataset.
D-003 | Guest Users | Temporary guest/debug customer records remain in the local DB. | 0799100003@guest.khalasni.local and 0799200003@guest.khalasni.local observed | Noise in reports, notifications, and manual flow review. | Clean test-only guest records during demo reset.
D-004 | Frontend Env Files | No frontend env files are present in the workspace. | frontend/.env and frontend/.env.local not found | Runtime base URL and feature toggles depend on code defaults instead of explicit config. | Add .env.example and project setup instructions.
D-005 | Build Output | Frontend build currently completes with a chunk-size warning. | vite build warning observed repeatedly | May become a production performance issue if left to grow. | Track bundle size in CI and split routes/components.
D-006 | Terminal Encoding | Arabic text can appear garbled in PowerShell/terminal inspection even when the file content is correct. | Observed during review/edit cycles on several JSX files | Debugging and manual code review become slower and more error-prone. | Standardize terminal/editor encoding settings for the team.