## Dashboard
Khalsni System Build Plan - Production Checklist
Generated: 2026-05-12
Area | Total Tasks | Not Started | In Progress | Blocked | Done | High Priority | Critical Priority
Backend Build | 16 | 0 | 0 | 0 | 16 | 3 | 12
UI Screens | 14 | 0 | 0 | 0 | 14 | 5 | 6
Workflow Logic | 10 | 0 | 0 | 0 | 10 | 3 | 7
Security Checklist | 11 | 0 | 2 | 0 | 9 | 1 | 9
Testing QA | 12 | 1 | 3 | 0 | 8 | 5 | 6
Deployment | 10 | 6 | 2 | 0 | 2 | 2 | 7
Missing Decisions | 10 | 2 | 4 | 0 | 4 | 5 | 2
Recommended Build Order
1 | Freeze models and migrations
2 | Seed roles, permissions, service categories, and demo data
3 | Implement selectors and permission helpers
4 | Implement workflow transition service and audit logs
5 | Implement document upload/verification security
6 | Implement notifications and reports
7 | Build UI screens using permission checks
8 | Write tests for roles, object access, workflow, and files
9 | Deploy staging with PostgreSQL, media storage, logs, backups
10 | User acceptance testing before production launch

## Master Roadmap
ID | Phase | Task | Details | App/Module | Output/Artifact | Priority | Status | Dependency | Acceptance Criteria
BE-001 | Foundation | Create Django app structure | Create apps: core, accounts, services, orders, documents, workflow, notifications, reports. Keep business logic out of views. | Project | Apps created and added to INSTALLED_APPS | Critical | Done |  | Project imports without errors
BE-002 | Foundation | Create core choices/constants | Define UserRole, OrderStatus, DocumentType, NotificationType, PaymentStatus, Priority constants using TextChoices. | core | core/choices.py | Critical | Done | BE-001 | No hardcoded status strings in models/services/views
BE-003 | Models | Finalize service models | ServiceCategory, Service, ServiceRequiredDocument, ServicePricingRule if needed. Include active flags and ordering. | services | services/models.py | Critical | Done | BE-002 | Admin can create service, define required docs, and deactivate service safely
BE-004 | Models | Finalize order models | Order, OrderAssignment, OrderNote, OrderStatusHistory or audit log fields. Include client, service, status, assigned employee/provider, dates, pricing fields. | orders | orders/models.py | Critical | Done | BE-002, BE-003 | Order lifecycle supports all workflow statuses
BE-005 | Models | Finalize document models | Secure file model with original filename, safe stored filename, MIME, size, document type, verification status, final document flag. | documents | documents/models.py | Critical | Done | BE-004 | Documents are linked to order and user, with verification state
BE-006 | Models | Create audit log model | Log actor, action, old_status, new_status, metadata, IP/user agent optional, timestamp. | orders/reports | OrderAuditLog model | Critical | Done | BE-004 | Every important order action creates audit log
BE-007 | Models | Create notification model | Recipient, title, message, related order, type, read flag, channel, timestamp. | notifications | Notification model | High | Done | BE-004 | Users can receive and read system notifications
BE-008 | Migrations | Run and review migrations | Generate migrations after model finalization; inspect SQL if needed before applying. | All apps | Migration files | Critical | Done | BE-003 to BE-007 | Migrations apply cleanly on empty DB
BE-009 | Permissions | Create role setup command | Create groups: client, employee, provider, admin. Assign permissions from production permission matrix. | accounts | setup_roles command | Critical | Done | BE-008 | Running command seeds all groups and permissions
BE-010 | Permissions | Create permission helpers | Reusable functions: is_admin, is_employee, is_provider, is_client, can_view_order, can_edit_order, can_download_document. | orders/documents | permissions.py | Critical | Done | BE-009 | No duplicated role logic in views/templates
BE-011 | Data Access | Create selectors | get_orders_for_user, get_documents_for_user, get_notifications_for_user. Enforce object-level access. | orders/documents | selectors.py | Critical | Done | BE-010 | Users never see unauthorized records
BE-012 | Services | Create order service layer | Functions for submit_order, review_order, request_missing_info, assign_provider, start_work, complete_provider_work, verify_order, deliver_order, cancel_order. | orders | services.py | Critical | Done | BE-011 | All status-changing actions go through service layer
BE-013 | Services | Create document service layer | Validate file type/size, upload required docs, verify/reject docs, upload final docs, secure download. | documents | services.py | Critical | Done | BE-005, BE-010 | Unsafe file uploads rejected; access checked before download
BE-014 | Services | Create notification service | notify_client, notify_employee, notify_provider, notify_admin. Called from order/document services. | notifications | services.py | High | Done | BE-007, BE-012 | Notifications are created automatically for important actions
BE-015 | Admin | Configure Django admin | Readable list_display, filters, search_fields, readonly audit fields, secure permissions. | All apps | admin.py | High | Done | BE-008 | Admin users can manage records safely
BE-016 | Seed Data | Create demo data command | Seed service categories, services, required documents, demo users for each role. | core/services | seed_demo command | Medium | Done | BE-009 | System can be tested end-to-end quickly
WF-001 | Status Engine | Define allowed transitions | Central transition map: draft→submitted, submitted→under_review, under_review→missing_info/assigned/rejected, etc. | workflow | rules.py | Critical | Done | BE-002 | No invalid transition can be saved
WF-002 | Status Engine | Create transition validator | validate_order_transition(current, next) with clear ValidationError. | workflow | services.py | Critical | Done | WF-001 | Invalid transitions raise error
WF-003 | Role Rules | Map transition permissions | Define which role can perform each transition; object ownership still checked. | workflow/orders | transition_permissions.py | Critical | Done | WF-001, BE-010 | Only authorized role can transition status
WF-004 | Atomic Updates | Wrap workflow actions in transactions | Use transaction.atomic for status updates, assignments, audit log, notification creation. | orders/workflow | service functions | Critical | Done | BE-012 | No partial update when error occurs
WF-005 | Missing Info Flow | Implement missing document request | Employee selects missing document type and note; client notification created; status becomes missing_info. | orders/documents | request_missing_info service | Critical | Done | WF-004, BE-014 | Client sees required missing documents
WF-006 | Assignment Flow | Implement provider assignment | Employee/admin assigns provider; provider notification created; order status assigned. | orders | assign_provider service | Critical | Done | WF-004 | Assigned provider can see order
WF-007 | Provider Flow | Implement provider completion | Provider starts work, uploads final document, marks completed_by_provider. | orders/documents | provider services | High | Done | WF-006, BE-013 | Final document linked and visible to employee/admin
WF-008 | Verification Flow | Implement final verification | Employee/admin reviews final document and sets verified/delivered or returns to missing_info/rework. | orders/documents | verify service | High | Done | WF-007 | Client notified when delivered
WF-009 | Cancellation Rules | Define cancellation rules | Client may cancel only draft/submitted; employee limited; admin can cancel most non-delivered orders. | workflow | cancellation service | High | Done | WF-003 | Cancellation follows business policy
WF-010 | Audit Trail | Log every transition | Every transition stores old/new status, actor, action, note, timestamp. | orders | audit service | Critical | Done | BE-006, WF-004 | Audit log complete for all status changes
SEC-001 | Auth | Require login everywhere | Protect all dashboard, order, document, notification, and report views with LoginRequiredMixin/decorators. | All views | login protection | Critical | Done | BE-009 | Anonymous users cannot access private screens
SEC-002 | Authorization | Server-side permission checks | Use PermissionRequiredMixin or explicit checks before every protected action. | All views/services | backend authorization | Critical | Done | BE-010 | Direct URL/API calls cannot bypass UI
SEC-003 | Object Access | Object-level filtering | Never use Order.objects.all() in user-facing views. Use selectors. | orders/documents | selectors enforced | Critical | Done | BE-011 | Users can access only permitted objects
SEC-004 | Files | Secure uploads | Validate extension, MIME, size; use generated safe filenames; block executable files. | documents | file validation | Critical | Done | BE-013 | Malicious/oversized files rejected
SEC-005 | Files | Secure downloads | Download endpoint checks can_view_document/can_download_document before serving file. | documents | download view | Critical | In Progress | BE-013 | Unauthorized file download returns 403/404
SEC-006 | CSRF | Enable CSRF protection | Use Django CSRF middleware and tokens in all forms. | Project/templates | CSRF enabled | Critical | Done | UI forms | POST without token rejected
SEC-007 | Forms | Use ModelForms with validation | Do not trust hidden fields for client/provider/price/status; set sensitive fields in backend. | All forms | forms.py | Critical | Done | BE-012 | User cannot tamper with status/ownership
SEC-008 | Admin | Restrict admin actions | Only staff/admin can access Django admin; readonly fields for audit fields. | admin | admin.py | High | Done | BE-015 | Non-admin roles blocked from admin
SEC-009 | Settings | Production security settings | Configure ALLOWED_HOSTS, CSRF_TRUSTED_ORIGINS, DEBUG=False, secure cookies, HSTS after HTTPS. | settings | production settings | Critical | In Progress | Deployment | Security checks pass
SEC-010 | Logging | Security logging | Log failed permission attempts and important actions without leaking sensitive data. | core | logging config | Medium | Done | SEC-002 | Suspicious actions visible in logs
SEC-011 | OWASP | Broken access control review | Manually test role bypass attempts: direct URLs, changing IDs, hidden button actions. | QA | security test checklist | Critical | Done | SEC-001 to SEC-005 | No broken access control found
UI-001 | Layout | Create base layout | Navbar/sidebar changes based on user role. Include notification icon and profile menu. | templates/core | base.html | Critical | Done | BE-009 | Only allowed navigation items appear
UI-002 | Client | Client dashboard | Show active orders, missing document requests, completed orders, recent notifications. | orders/templates | client_dashboard.html | High | Done | BE-011 | Client only sees own data
UI-003 | Client | Create order screen | Service selection, dynamic required documents, notes, submit as draft/submitted. | orders/templates | order_form.html | Critical | Done | BE-003, BE-012 | Client can create valid order
UI-004 | Client | My orders screen | List own orders with status, date, service, next required action. | orders/templates | my_orders.html | High | Done | BE-011 | No other users' orders shown
UI-005 | Client | Missing documents response screen | Upload requested documents and resubmit order. | documents/templates | missing_docs.html | Critical | Done | BE-013 | Upload only allowed while order is missing_info
UI-006 | Employee | Employee review queue | Show submitted/resubmitted orders needing review. | orders/templates | employee_queue.html | Critical | Done | BE-011, BE-012 | Employee can review allowed orders
UI-007 | Employee | Order review detail | Actions: request missing docs, reject, assign provider, add note, verify documents. | orders/templates | employee_order_detail.html | Critical | Done | BE-012, BE-013 | Every button maps to protected backend action
UI-008 | Provider | Provider assigned orders | Show provider's assigned orders only. | orders/templates | provider_orders.html | High | Done | BE-011 | Provider sees assigned orders only
UI-009 | Provider | Provider work detail | Actions: start work, update work note, upload final document, mark completed. | orders/documents templates | provider_order_detail.html | Critical | Done | BE-012, BE-013 | Provider can update only assigned active orders
UI-010 | Admin | Admin reports dashboard | High-level counts, orders by status, service volume, provider performance, missing documents. | reports/templates | reports_dashboard.html | High | Done | BE-006, BE-011 | Admin sees full reporting
UI-011 | Admin | Manage services/prices screens | CRUD service categories, services, required documents, pricing. | services/templates | service_admin.html | High | Done | BE-003 | Only admin can modify services/prices
UI-012 | Admin | Manage users/roles screen | Assign users to roles/groups; view active/inactive users. | accounts/templates | user_admin.html | Medium | Done | BE-009 | Only admin can change roles
UI-013 | Shared | Order timeline component | Reusable timeline showing status history, notes, and audit events according to access. | orders/templates/partials | _order_timeline.html | Medium | Done | BE-006 | Timeline is correct and safe for each role
UI-014 | Shared | Notification center | List notifications, mark read, link to related order where allowed. | notifications/templates | notifications.html | Medium | Done | BE-014 | Unauthorized order links are blocked
QA-001 | Unit Tests | Test role helpers | Test is_admin/is_employee/is_provider/is_client and permission helper behavior. | accounts/orders | test_permissions.py | Critical | Done | BE-010 | Role helper tests pass
QA-002 | Unit Tests | Test selectors | Each role sees only expected orders/documents/notifications. | orders/documents | test_selectors.py | Critical | Done | BE-011 | No unauthorized records returned
QA-003 | Unit Tests | Test workflow transitions | Allowed transitions pass; invalid transitions fail. | workflow | test_workflow.py | Critical | Done | WF-001, WF-002 | Transition tests pass
QA-004 | Integration Tests | Test client order flow | Client creates order, uploads docs, submits, sees own timeline. | orders/documents | client flow test | High | Done | UI-003 | End-to-end client flow passes
QA-005 | Integration Tests | Test employee review flow | Employee reviews, requests missing info, assigns provider, verifies final output. | orders | employee flow test | High | Done | UI-006, UI-007 | Employee flow passes
QA-006 | Integration Tests | Test provider flow | Provider sees assigned order, starts work, uploads final document, completes. | orders/documents | provider flow test | High | Done | UI-008, UI-009 | Provider flow passes
QA-007 | Security Tests | Test direct URL bypass | Try opening another client's order/document using ID manipulation. | All views | access control test | Critical | Done | SEC-003, SEC-005 | Unauthorized access blocked
QA-008 | Security Tests | Test file upload attacks | Try invalid extensions, large files, wrong MIME, dangerous names. | documents | file upload test | Critical | In Progress | SEC-004 | Bad files rejected
QA-009 | UI Tests | Manual role UI review | Login as each role and verify visible screens/buttons match permission matrix. | templates | manual QA checklist | High | In Progress | UI-001 to UI-014 | UI matches backend permissions
QA-010 | Data Tests | Audit log completeness | Check each action creates correct audit log record. | orders | audit tests | High | Done | WF-010 | Audit log present for all important actions
QA-011 | Performance | Basic query performance review | Use select_related/prefetch_related on order lists and detail pages. | orders | query optimization | Medium | In Progress | UI lists | No excessive duplicate queries
QA-012 | UAT | User acceptance testing | Test real business scenarios with admin/employee/provider/client accounts. | Project | UAT signoff | Critical | Not Started | All core features | Client confirms flow is correct
DEP-001 | Environment | Create .env structure | SECRET_KEY, DEBUG, DATABASE_URL, ALLOWED_HOSTS, CSRF_TRUSTED_ORIGINS, EMAIL settings, media path. | Project | .env.example | Critical | Done | BE complete | Settings loaded from environment
DEP-002 | Database | Use PostgreSQL | Configure PostgreSQL for staging/production; avoid SQLite in production. | settings/db | database config | Critical | Done | DEP-001 | Migrations run on PostgreSQL
DEP-003 | Static Files | Configure static files | Use collectstatic and WhiteNoise or reverse proxy static serving. | Project | static config | High | In Progress | DEP-001 | Static assets load in production
DEP-004 | Media Files | Configure media storage | Local protected media for MVP or S3-compatible storage later; document backup path. | documents | media config | Critical | In Progress | SEC-005 | Uploaded files persist and are protected
DEP-005 | Email | Configure email backend | SMTP settings for notifications/password reset. Database notifications remain primary. | notifications | email config | Medium | Not Started | BE-014 | Test email sends successfully
DEP-006 | Backups | Create backup plan | Database daily backups + media backup + restore test. | Ops | backup procedure | Critical | Not Started | DEP-002, DEP-004 | Restore test succeeds
DEP-007 | Logging | Configure production logging | App logs, error logs, access logs; avoid sensitive data in logs. | Project | logging config | High | Not Started | SEC-010 | Errors traceable in production
DEP-008 | Staging | Deploy staging environment | Use Coolify/Docker or VPS setup with domain, HTTPS, env vars, DB, media. | Ops | staging deployment | Critical | Not Started | DEP-001 to DEP-007 | Staging accessible over HTTPS
DEP-009 | Security | Run Django deployment checks | Run python manage.py check --deploy and fix warnings. | Project | deployment check report | Critical | Not Started | DEP-008 | No critical deployment warnings
DEP-010 | Release | Production launch checklist | Migrations, roles seed, admin user, service seed, backups, monitoring, smoke tests. | Ops | release checklist | Critical | Not Started | QA-012, DEP-009 | Production smoke test passes
DEC-001 | Business Rule | Who can assign provider? | Decide if employee can assign any provider or only admin can assign providers. | orders | policy decision | High | Done |  | Documented rule and implemented permission
DEC-002 | Business Rule | Can employee see all orders? | Decide if employees see all submitted orders or only orders assigned to them. | orders | policy decision | Critical | Done |  | Selector logic matches decision
DEC-003 | Business Rule | Payment handling | Decide if payment is external/manual report only or integrated payment gateway. | payments/reports | payment scope | High | In Progress |  | Payment status model or report flow finalized
DEC-004 | Business Rule | Cancellation/refund rules | Define when clients can cancel and whether payment/refund status changes. | orders/payments | policy decision | High | In Progress |  | Cancellation rules implemented and tested
DEC-005 | Documents | Allowed file types and max size | Define accepted types: PDF/JPG/PNG/docx? Max MB per file. | documents | file policy | Critical | Done |  | Upload validation constants finalized
DEC-006 | Documents | Document retention policy | Define how long to keep uploaded files and audit logs. | documents/legal | retention policy | Medium | Not Started |  | Retention policy documented
DEC-007 | Notifications | Notification channels | Choose MVP channels: internal only, email, SMS, WhatsApp later. | notifications | channel decision | Medium | In Progress |  | Notification service supports selected channels
DEC-008 | Reports | Required reports | Define reports needed by admin: order volume, status aging, provider performance, revenue/payment report. | reports | report list | High | Done |  | Reports dashboard scope finalized
DEC-009 | Localization | Arabic/English support | Decide whether MVP needs bilingual UI and data fields for all services/messages. | templates/models | language decision | Medium | In Progress |  | UI/message localization plan selected
DEC-010 | Deployment | Hosting target | Decide VPS/Coolify, domain/subdomain, backup location, email provider. | Ops | deployment decision | High | Not Started |  | Staging deployment plan finalized

## Backend Build
ID | Phase | Task | Details | App/Module | Output/Artifact | Priority | Status | Dependency | Acceptance Criteria
BE-001 | Foundation | Create Django app structure | Create apps: core, accounts, services, orders, documents, workflow, notifications, reports. Keep business logic out of views. | Project | Apps created and added to INSTALLED_APPS | Critical | Done |  | Project imports without errors
BE-002 | Foundation | Create core choices/constants | Define UserRole, OrderStatus, DocumentType, NotificationType, PaymentStatus, Priority constants using TextChoices. | core | core/choices.py | Critical | Done | BE-001 | No hardcoded status strings in models/services/views
BE-003 | Models | Finalize service models | ServiceCategory, Service, ServiceRequiredDocument, ServicePricingRule if needed. Include active flags and ordering. | services | services/models.py | Critical | Done | BE-002 | Admin can create service, define required docs, and deactivate service safely
BE-004 | Models | Finalize order models | Order, OrderAssignment, OrderNote, OrderStatusHistory or audit log fields. Include client, service, status, assigned employee/provider, dates, pricing fields. | orders | orders/models.py | Critical | Done | BE-002, BE-003 | Order lifecycle supports all workflow statuses
BE-005 | Models | Finalize document models | Secure file model with original filename, safe stored filename, MIME, size, document type, verification status, final document flag. | documents | documents/models.py | Critical | Done | BE-004 | Documents are linked to order and user, with verification state
BE-006 | Models | Create audit log model | Log actor, action, old_status, new_status, metadata, IP/user agent optional, timestamp. | orders/reports | OrderAuditLog model | Critical | Done | BE-004 | Every important order action creates audit log
BE-007 | Models | Create notification model | Recipient, title, message, related order, type, read flag, channel, timestamp. | notifications | Notification model | High | Done | BE-004 | Users can receive and read system notifications
BE-008 | Migrations | Run and review migrations | Generate migrations after model finalization; inspect SQL if needed before applying. | All apps | Migration files | Critical | Done | BE-003 to BE-007 | Migrations apply cleanly on empty DB
BE-009 | Permissions | Create role setup command | Create groups: client, employee, provider, admin. Assign permissions from production permission matrix. | accounts | setup_roles command | Critical | Done | BE-008 | Running command seeds all groups and permissions
BE-010 | Permissions | Create permission helpers | Reusable functions: is_admin, is_employee, is_provider, is_client, can_view_order, can_edit_order, can_download_document. | orders/documents | permissions.py | Critical | Done | BE-009 | No duplicated role logic in views/templates
BE-011 | Data Access | Create selectors | get_orders_for_user, get_documents_for_user, get_notifications_for_user. Enforce object-level access. | orders/documents | selectors.py | Critical | Done | BE-010 | Users never see unauthorized records
BE-012 | Services | Create order service layer | Functions for submit_order, review_order, request_missing_info, assign_provider, start_work, complete_provider_work, verify_order, deliver_order, cancel_order. | orders | services.py | Critical | Done | BE-011 | All status-changing actions go through service layer
BE-013 | Services | Create document service layer | Validate file type/size, upload required docs, verify/reject docs, upload final docs, secure download. | documents | services.py | Critical | Done | BE-005, BE-010 | Unsafe file uploads rejected; access checked before download
BE-014 | Services | Create notification service | notify_client, notify_employee, notify_provider, notify_admin. Called from order/document services. | notifications | services.py | High | Done | BE-007, BE-012 | Notifications are created automatically for important actions
BE-015 | Admin | Configure Django admin | Readable list_display, filters, search_fields, readonly audit fields, secure permissions. | All apps | admin.py | High | Done | BE-008 | Admin users can manage records safely
BE-016 | Seed Data | Create demo data command | Seed service categories, services, required documents, demo users for each role. | core/services | seed_demo command | Medium | Done | BE-009 | System can be tested end-to-end quickly

## UI Screens
ID | Phase | Task | Details | App/Module | Output/Artifact | Priority | Status | Dependency | Acceptance Criteria
UI-001 | Layout | Create base layout | Navbar/sidebar changes based on user role. Include notification icon and profile menu. | templates/core | base.html | Critical | Done | BE-009 | Only allowed navigation items appear
UI-002 | Client | Client dashboard | Show active orders, missing document requests, completed orders, recent notifications. | orders/templates | client_dashboard.html | High | Done | BE-011 | Client only sees own data
UI-003 | Client | Create order screen | Service selection, dynamic required documents, notes, submit as draft/submitted. | orders/templates | order_form.html | Critical | Done | BE-003, BE-012 | Client can create valid order
UI-004 | Client | My orders screen | List own orders with status, date, service, next required action. | orders/templates | my_orders.html | High | Done | BE-011 | No other users' orders shown
UI-005 | Client | Missing documents response screen | Upload requested documents and resubmit order. | documents/templates | missing_docs.html | Critical | Done | BE-013 | Upload only allowed while order is missing_info
UI-006 | Employee | Employee review queue | Show submitted/resubmitted orders needing review. | orders/templates | employee_queue.html | Critical | Done | BE-011, BE-012 | Employee can review allowed orders
UI-007 | Employee | Order review detail | Actions: request missing docs, reject, assign provider, add note, verify documents. | orders/templates | employee_order_detail.html | Critical | Done | BE-012, BE-013 | Every button maps to protected backend action
UI-008 | Provider | Provider assigned orders | Show provider's assigned orders only. | orders/templates | provider_orders.html | High | Done | BE-011 | Provider sees assigned orders only
UI-009 | Provider | Provider work detail | Actions: start work, update work note, upload final document, mark completed. | orders/documents templates | provider_order_detail.html | Critical | Done | BE-012, BE-013 | Provider can update only assigned active orders
UI-010 | Admin | Admin reports dashboard | High-level counts, orders by status, service volume, provider performance, missing documents. | reports/templates | reports_dashboard.html | High | Done | BE-006, BE-011 | Admin sees full reporting
UI-011 | Admin | Manage services/prices screens | CRUD service categories, services, required documents, pricing. | services/templates | service_admin.html | High | Done | BE-003 | Only admin can modify services/prices
UI-012 | Admin | Manage users/roles screen | Assign users to roles/groups; view active/inactive users. | accounts/templates | user_admin.html | Medium | Done | BE-009 | Only admin can change roles
UI-013 | Shared | Order timeline component | Reusable timeline showing status history, notes, and audit events according to access. | orders/templates/partials | _order_timeline.html | Medium | Done | BE-006 | Timeline is correct and safe for each role
UI-014 | Shared | Notification center | List notifications, mark read, link to related order where allowed. | notifications/templates | notifications.html | Medium | Done | BE-014 | Unauthorized order links are blocked

## Workflow Logic
ID | Phase | Task | Details | App/Module | Output/Artifact | Priority | Status | Dependency | Acceptance Criteria
WF-001 | Status Engine | Define allowed transitions | Central transition map: draft→submitted, submitted→under_review, under_review→missing_info/assigned/rejected, etc. | workflow | rules.py | Critical | Done | BE-002 | No invalid transition can be saved
WF-002 | Status Engine | Create transition validator | validate_order_transition(current, next) with clear ValidationError. | workflow | services.py | Critical | Done | WF-001 | Invalid transitions raise error
WF-003 | Role Rules | Map transition permissions | Define which role can perform each transition; object ownership still checked. | workflow/orders | transition_permissions.py | Critical | Done | WF-001, BE-010 | Only authorized role can transition status
WF-004 | Atomic Updates | Wrap workflow actions in transactions | Use transaction.atomic for status updates, assignments, audit log, notification creation. | orders/workflow | service functions | Critical | Done | BE-012 | No partial update when error occurs
WF-005 | Missing Info Flow | Implement missing document request | Employee selects missing document type and note; client notification created; status becomes missing_info. | orders/documents | request_missing_info service | Critical | Done | WF-004, BE-014 | Client sees required missing documents
WF-006 | Assignment Flow | Implement provider assignment | Employee/admin assigns provider; provider notification created; order status assigned. | orders | assign_provider service | Critical | Done | WF-004 | Assigned provider can see order
WF-007 | Provider Flow | Implement provider completion | Provider starts work, uploads final document, marks completed_by_provider. | orders/documents | provider services | High | Done | WF-006, BE-013 | Final document linked and visible to employee/admin
WF-008 | Verification Flow | Implement final verification | Employee/admin reviews final document and sets verified/delivered or returns to missing_info/rework. | orders/documents | verify service | High | Done | WF-007 | Client notified when delivered
WF-009 | Cancellation Rules | Define cancellation rules | Client may cancel only draft/submitted; employee limited; admin can cancel most non-delivered orders. | workflow | cancellation service | High | Done | WF-003 | Cancellation follows business policy
WF-010 | Audit Trail | Log every transition | Every transition stores old/new status, actor, action, note, timestamp. | orders | audit service | Critical | Done | BE-006, WF-004 | Audit log complete for all status changes

## Security Checklist
ID | Phase | Task | Details | App/Module | Output/Artifact | Priority | Status | Dependency | Acceptance Criteria
SEC-001 | Auth | Require login everywhere | Protect all dashboard, order, document, notification, and report views with LoginRequiredMixin/decorators. | All views | login protection | Critical | Done | BE-009 | Anonymous users cannot access private screens
SEC-002 | Authorization | Server-side permission checks | Use PermissionRequiredMixin or explicit checks before every protected action. | All views/services | backend authorization | Critical | Done | BE-010 | Direct URL/API calls cannot bypass UI
SEC-003 | Object Access | Object-level filtering | Never use Order.objects.all() in user-facing views. Use selectors. | orders/documents | selectors enforced | Critical | Done | BE-011 | Users can access only permitted objects
SEC-004 | Files | Secure uploads | Validate extension, MIME, size; use generated safe filenames; block executable files. | documents | file validation | Critical | Done | BE-013 | Malicious/oversized files rejected
SEC-005 | Files | Secure downloads | Download endpoint checks can_view_document/can_download_document before serving file. | documents | download view | Critical | In Progress | BE-013 | Unauthorized file download returns 403/404
SEC-006 | CSRF | Enable CSRF protection | Use Django CSRF middleware and tokens in all forms. | Project/templates | CSRF enabled | Critical | Done | UI forms | POST without token rejected
SEC-007 | Forms | Use ModelForms with validation | Do not trust hidden fields for client/provider/price/status; set sensitive fields in backend. | All forms | forms.py | Critical | Done | BE-012 | User cannot tamper with status/ownership
SEC-008 | Admin | Restrict admin actions | Only staff/admin can access Django admin; readonly fields for audit fields. | admin | admin.py | High | Done | BE-015 | Non-admin roles blocked from admin
SEC-009 | Settings | Production security settings | Configure ALLOWED_HOSTS, CSRF_TRUSTED_ORIGINS, DEBUG=False, secure cookies, HSTS after HTTPS. | settings | production settings | Critical | In Progress | Deployment | Security checks pass
SEC-010 | Logging | Security logging | Log failed permission attempts and important actions without leaking sensitive data. | core | logging config | Medium | Done | SEC-002 | Suspicious actions visible in logs
SEC-011 | OWASP | Broken access control review | Manually test role bypass attempts: direct URLs, changing IDs, hidden button actions. | QA | security test checklist | Critical | Done | SEC-001 to SEC-005 | No broken access control found

## Testing QA
ID | Phase | Task | Details | App/Module | Output/Artifact | Priority | Status | Dependency | Acceptance Criteria
QA-001 | Unit Tests | Test role helpers | Test is_admin/is_employee/is_provider/is_client and permission helper behavior. | accounts/orders | test_permissions.py | Critical | Done | BE-010 | Role helper tests pass
QA-002 | Unit Tests | Test selectors | Each role sees only expected orders/documents/notifications. | orders/documents | test_selectors.py | Critical | Done | BE-011 | No unauthorized records returned
QA-003 | Unit Tests | Test workflow transitions | Allowed transitions pass; invalid transitions fail. | workflow | test_workflow.py | Critical | Done | WF-001, WF-002 | Transition tests pass
QA-004 | Integration Tests | Test client order flow | Client creates order, uploads docs, submits, sees own timeline. | orders/documents | client flow test | High | Done | UI-003 | End-to-end client flow passes
QA-005 | Integration Tests | Test employee review flow | Employee reviews, requests missing info, assigns provider, verifies final output. | orders | employee flow test | High | Done | UI-006, UI-007 | Employee flow passes
QA-006 | Integration Tests | Test provider flow | Provider sees assigned order, starts work, uploads final document, completes. | orders/documents | provider flow test | High | Done | UI-008, UI-009 | Provider flow passes
QA-007 | Security Tests | Test direct URL bypass | Try opening another client's order/document using ID manipulation. | All views | access control test | Critical | Done | SEC-003, SEC-005 | Unauthorized access blocked
QA-008 | Security Tests | Test file upload attacks | Try invalid extensions, large files, wrong MIME, dangerous names. | documents | file upload test | Critical | In Progress | SEC-004 | Bad files rejected
QA-009 | UI Tests | Manual role UI review | Login as each role and verify visible screens/buttons match permission matrix. | templates | manual QA checklist | High | In Progress | UI-001 to UI-014 | UI matches backend permissions
QA-010 | Data Tests | Audit log completeness | Check each action creates correct audit log record. | orders | audit tests | High | Done | WF-010 | Audit log present for all important actions
QA-011 | Performance | Basic query performance review | Use select_related/prefetch_related on order lists and detail pages. | orders | query optimization | Medium | In Progress | UI lists | No excessive duplicate queries
QA-012 | UAT | User acceptance testing | Test real business scenarios with admin/employee/provider/client accounts. | Project | UAT signoff | Critical | Not Started | All core features | Client confirms flow is correct

## Deployment
ID | Phase | Task | Details | App/Module | Output/Artifact | Priority | Status | Dependency | Acceptance Criteria
DEP-001 | Environment | Create .env structure | SECRET_KEY, DEBUG, DATABASE_URL, ALLOWED_HOSTS, CSRF_TRUSTED_ORIGINS, EMAIL settings, media path. | Project | .env.example | Critical | Done | BE complete | Settings loaded from environment
DEP-002 | Database | Use PostgreSQL | Configure PostgreSQL for staging/production; avoid SQLite in production. | settings/db | database config | Critical | Done | DEP-001 | Migrations run on PostgreSQL
DEP-003 | Static Files | Configure static files | Use collectstatic and WhiteNoise or reverse proxy static serving. | Project | static config | High | In Progress | DEP-001 | Static assets load in production
DEP-004 | Media Files | Configure media storage | Local protected media for MVP or S3-compatible storage later; document backup path. | documents | media config | Critical | In Progress | SEC-005 | Uploaded files persist and are protected
DEP-005 | Email | Configure email backend | SMTP settings for notifications/password reset. Database notifications remain primary. | notifications | email config | Medium | Not Started | BE-014 | Test email sends successfully
DEP-006 | Backups | Create backup plan | Database daily backups + media backup + restore test. | Ops | backup procedure | Critical | Not Started | DEP-002, DEP-004 | Restore test succeeds
DEP-007 | Logging | Configure production logging | App logs, error logs, access logs; avoid sensitive data in logs. | Project | logging config | High | Not Started | SEC-010 | Errors traceable in production
DEP-008 | Staging | Deploy staging environment | Use Coolify/Docker or VPS setup with domain, HTTPS, env vars, DB, media. | Ops | staging deployment | Critical | Not Started | DEP-001 to DEP-007 | Staging accessible over HTTPS
DEP-009 | Security | Run Django deployment checks | Run python manage.py check --deploy and fix warnings. | Project | deployment check report | Critical | Not Started | DEP-008 | No critical deployment warnings
DEP-010 | Release | Production launch checklist | Migrations, roles seed, admin user, service seed, backups, monitoring, smoke tests. | Ops | release checklist | Critical | Not Started | QA-012, DEP-009 | Production smoke test passes

## Missing Decisions
ID | Phase | Task | Details | App/Module | Output/Artifact | Priority | Status | Dependency | Acceptance Criteria
DEC-001 | Business Rule | Who can assign provider? | Decide if employee can assign any provider or only admin can assign providers. | orders | policy decision | High | Done |  | Documented rule and implemented permission
DEC-002 | Business Rule | Can employee see all orders? | Decide if employees see all submitted orders or only orders assigned to them. | orders | policy decision | Critical | Done |  | Selector logic matches decision
DEC-003 | Business Rule | Payment handling | Decide if payment is external/manual report only or integrated payment gateway. | payments/reports | payment scope | High | In Progress |  | Payment status model or report flow finalized
DEC-004 | Business Rule | Cancellation/refund rules | Define when clients can cancel and whether payment/refund status changes. | orders/payments | policy decision | High | In Progress |  | Cancellation rules implemented and tested
DEC-005 | Documents | Allowed file types and max size | Define accepted types: PDF/JPG/PNG/docx? Max MB per file. | documents | file policy | Critical | Done |  | Upload validation constants finalized
DEC-006 | Documents | Document retention policy | Define how long to keep uploaded files and audit logs. | documents/legal | retention policy | Medium | Not Started |  | Retention policy documented
DEC-007 | Notifications | Notification channels | Choose MVP channels: internal only, email, SMS, WhatsApp later. | notifications | channel decision | Medium | In Progress |  | Notification service supports selected channels
DEC-008 | Reports | Required reports | Define reports needed by admin: order volume, status aging, provider performance, revenue/payment report. | reports | report list | High | Done |  | Reports dashboard scope finalized
DEC-009 | Localization | Arabic/English support | Decide whether MVP needs bilingual UI and data fields for all services/messages. | templates/models | language decision | Medium | In Progress |  | UI/message localization plan selected
DEC-010 | Deployment | Hosting target | Decide VPS/Coolify, domain/subdomain, backup location, email provider. | Ops | deployment decision | High | Not Started |  | Staging deployment plan finalized